## Power BI Output - MCIP
Project ID | Project Name | WBS | Activity Name | Start Date | Finish Date | Budgeted Total Cost | Actual Total Cost | Remaining Total Cost | MCIP Community | MCIP P.O. #
WS-MCIP-2018 | MCIP - 2018 | Village of Richfield--Briarwood Area Wastewater Pump Stations | Design Phase | 01/01/2018 A | 04/20/2021 A | 0 | 0 | 0 | Village of Richfield | 18004746
WS-MCIP-2020 | MCIP - 2020 | Berea - North End Phase 2 | Design Phase | 03/01/2019 A | 05/17/2019 A | 0 | 0 | 0 | Berea | 20000057
WS-MCIP-2021 | MCIP - 2021 | Lorain - Westview I&I Remediation | Design Phase | 10/01/2020 A | 01/15/2021 A | 0 | 0 | 0 | Lorain County | 20007975
WS-MCIP-2017 | MCIP - 2017 | Seven Hills- Hemlock Creek Watershed Utiltiy Improvement | Construction Phase | 01/01/2017 A | 12/20/2019 A | 0 | 0 | 0 | Seven Hills | 17004258
WS-MCIP-2018 | MCIP - 2018 | Village of Richfield--Briarwood Area Wastewater Pump Stations | Construction Phase | 09/02/2021* | 2022-05-19 | 0 | 0 | 0 | Village of Richfield | 18004746
WS-MCIP-2020 | MCIP - 2020 | Berea - North End Phase 2 | Construction Phase | 04/15/2020 A | 2022-12-20 | 0 | 0 | 0 | Berea | 20000057
WS-MCIP-2021 | MCIP - 2021 | Lorain - Westview I&I Remediation | Construction Phase | 06/01/2021 A | 2021-10-25 | 0 | 0 | 0 | Lorain County | 20007975
WS-MCIP-2017 | MCIP - 2017 | Olmsted Falls - Columbia & Cook Sanitary Sewer Project Phase 5 | Design Phase | 01/01/2017 A | 10/01/2017 A | 0 | 0 | 0 | Olmsted Falls | 17004905
WS-MCIP-2018 | MCIP - 2018 | Mayfield Village--Thornapple Drive & Robley Lane New Sanitary Sewer | Design Phase | 01/01/2018 A | 02/28/2018 A | 0 | 0 | 0 | Mayfield Village | 18001614
WS-MCIP-2019 | MCIP - 2019 | Brecksville-Chippewa Road Sanitary Sewer Project | Design Phase | 01/01/2019 A | 10/19/2019 A | 0 | 0 | 0 | Brecksville | 18007901
WS-MCIP-2020 | MCIP - 2020 | Summit County-Macedonia - Crow Berkshire Private I/I | Design Phase | 03/02/2020 A | 2021-12-25 | 0 | 0 | 0 | Summit County | 20001661
WS-MCIP-2021 | MCIP - 2021 | Maple Heights Southwest Area - Design Only | Design Phase | 03/01/2021 A | 2021-12-14 | 0 | 0 | 0 | Maple Heights | 21002394
WS-MCIP-2017 | MCIP - 2017 | Olmsted Falls - Columbia & Cook Sanitary Sewer Project Phase 5 | Construction Phase | 12/01/2017 A | 05/18/2020 A | 0 | 0 | 0 | Olmsted Falls | 17004905
WS-MCIP-2018 | MCIP - 2018 | Mayfield Village--Thornapple Drive & Robley Lane New Sanitary Sewer | Construction Phase | 03/19/2018 A | 05/20/2019 A | 0 | 0 | 0 | Mayfield Village | 18001614
WS-MCIP-2019 | MCIP - 2019 | Brecksville-Chippewa Road Sanitary Sewer Project | Construction Phase | 10/31/2020 A | 2023-06-30 | 0 | 0 | 0 | Brecksville | 18007901
WS-MCIP-2020 | MCIP - 2020 | Summit County-Macedonia - Crow Berkshire Private I/I | Construction Phase | 04/01/2022* | 2022-12-25 | 0 | 0 | 0 | Summit County | 20001661
WS-MCIP-2021 | MCIP - 2021 | Maple Heights Southwest Area - Design Only | Construction Phase | 09/19/2021* | 2022-07-17 | 0 | 0 | 0 | Maple Heights | 21002394
WS-MCIP-2020 | MCIP - 2020 | Summit County-Macedonia - Crow Berkshire Private I/I | Pre-Verification | 03/01/2020 A | 06/10/2020 A | 0 | 0 | 0 | Summit County | 20001661
WS-MCIP-2021 | MCIP - 2021 | Maple Heights Southwest Area - Design Only | Pre-Verification | 03/12/2019 A | 05/15/2019 A | 0 | 0 | 0 | Maple Heights | 21002394
WS-MCIP-2020 | MCIP - 2020 | Summit County-Macedonia - Crow Berkshire Private I/I | Post-Verification | 12/26/2022* | 2023-02-25 | 0 | 0 | 0 | Summit County | 20001661
WS-MCIP-2021 | MCIP - 2021 | Maple Heights Southwest Area - Design Only | Post-Verification | 09/15/2022* | 2022-10-15 | 0 | 0 | 0 | Maple Heights | 21002394
WS-MCIP-2017 | MCIP - 2017 | South Euclid - Grosvenor Infrastructure Improvement, Phase 2 | Design Phase | 01/01/2017 A | 01/26/2017 A | 0 | 0 | 0 | South Euclid | 17003621
WS-MCIP-2018 | MCIP - 2018 | Parma--Brookdale/Broadview Septic Systems Abatement Project | Design Phase | 01/01/2018 A | 04/17/2019 A | 0 | 0 | 0 | Parma | 18003716
WS-MCIP-2019 | MCIP - 2019 | CCDPW-Bagley and Cook Roads Sewer Connections | Design Phase | 01/01/2019 A | 01/01/2019 A | 0 | 0 | 0 | Cuyahoga County | 19000821
WS-MCIP-2020 | MCIP - 2020 | Parma - Sprague Road | Design Phase | 01/01/2020 A | 09/01/2020 A | 0 | 0 | 0 | Parma | 19008576
WS-MCIP-2021 | MCIP - 2021 | South Euclid - Oakmount Rd | Design Phase | 01/01/2020 A | 05/01/2020 A | 0 | 0 | 0 | South Euclid | 21002397
WS-MCIP-2017 | MCIP - 2017 | South Euclid - Grosvenor Infrastructure Improvement, Phase 2 | Construction Phase | 04/03/2017 A | 07/11/2017 A | 0 | 0 | 0 | South Euclid | 17003621
WS-MCIP-2018 | MCIP - 2018 | Parma--Brookdale/Broadview Septic Systems Abatement Project | Construction Phase | 06/01/2019 A | 12/01/2019 A | 0 | 0 | 0 | Parma | 18003716
WS-MCIP-2019 | MCIP - 2019 | CCDPW-Bagley and Cook Roads Sewer Connections | Construction Phase | 09/10/2019 A | 2021-12-30 | 0 | 0 | 0 | Cuyahoga County | 19000821
WS-MCIP-2020 | MCIP - 2020 | Parma - Sprague Road | Construction Phase | 07/01/2021* | 2022-12-25 | 0 | 0 | 0 | Parma | 19008576
WS-MCIP-2021 | MCIP - 2021 | South Euclid - Oakmount Rd | Construction Phase | 03/01/2021 A | 2021-10-31 | 0 | 0 | 0 | South Euclid | 21002397
WS-MCIP-2017 | MCIP - 2017 | Newburgh Heights - East 54th and Brow Avenue Sewer Separation | Design Phase | 01/01/2017 A | 04/27/2017 A | 0 | 0 | 0 | Newburgh Heights | 17002792
WS-MCIP-2018 | MCIP - 2018 | Garfield Heights--Midwest Neighborhood Storm/Sanitary Sewer Recon. Phase 2 | Design Phase | 01/01/2018 A | 07/01/2018 A | 0 | 0 | 0 | Garfield Heights | 18000954
WS-MCIP-2020 | MCIP - 2020 | Cleveland Heights - Delamere Drive Basement Flooding Relief | Design Phase | 04/01/2020 A | 10/31/2020 A | 0 | 0 | 0 | Cleveland Heights | 19008773
WS-MCIP-2021 | MCIP - 2021 | East Cleveland Wheeler Ave - Design Only | Design Phase | 01/01/2021 A | 2021-12-31 | 0 | 0 | 0 | East Cleveland | 21000321
WS-MCIP-2017 | MCIP - 2017 | Newburgh Heights - East 54th and Brow Avenue Sewer Separation | Construction Phase | 05/05/2017 A | 10/30/2017 A | 0 | 0 | 0 | Newburgh Heights | 17002792
WS-MCIP-2018 | MCIP - 2018 | Garfield Heights--Midwest Neighborhood Storm/Sanitary Sewer Recon. Phase 2 | Construction Phase | 01/21/2019 A | 10/01/2019 A | 0 | 0 | 0 | Garfield Heights | 18000954
WS-MCIP-2020 | MCIP - 2020 | Cleveland Heights - Delamere Drive Basement Flooding Relief | Construction Phase | 03/01/2021 A | 05/25/2021 A | 0 | 0 | 0 | Cleveland Heights | 19008773
WS-MCIP-2020 | MCIP - 2020 | Cleveland Heights - Delamere Drive Basement Flooding Relief | Pre-Verification | 09/10/2018 A | 11/15/2018 A | 0 | 0 | 0 | Cleveland Heights | 19008773
WS-MCIP-2021 | MCIP - 2021 | East Cleveland Wheeler Ave - Design Only | Pre-Verification | 05/04/2021 A | 2021-08-04 | 0 | 0 | 0 | East Cleveland | 21000321
WS-MCIP-2020 | MCIP - 2020 | Cleveland Heights - Delamere Drive Basement Flooding Relief | Post-Verification | 08/01/2021* | 2021-10-01 | 0 | 0 | 0 | Cleveland Heights | 19008773
WS-MCIP-2017 | MCIP - 2017 | Garfield Heights - NW Neighborhood Sanitary/Storm Sewer Reconstruction Phase 1 | Design Phase | 01/01/2017 A | 10/30/2017 A | 0 | 0 | 0 | Garfield Heights | 17004331
WS-MCIP-2018 | MCIP - 2018 | Maple Heights--Milan/Harlan Drive Sanitary Replacement Project | Design Phase | 01/01/2018 A | 08/08/2018 A | 0 | 0 | 0 | Maple Heights | 18005835
WS-MCIP-2020 | MCIP - 2020 | Maple Heights - Southwest Sewer District Sewer Improvements Phase 1 | Design Phase | 01/01/2020 A | 11/20/2020 A | 0 | 0 | 0 | Maple Heights | 20003342
WS-MCIP-2021 | MCIP - 2021 | Parma Green Acres - Design Only | Design Phase | 01/01/2021 A | 2021-12-31 | 0 | 0 | 0 | Parma | 21000571
WS-MCIP-2017 | MCIP - 2017 | Garfield Heights - NW Neighborhood Sanitary/Storm Sewer Reconstruction Phase 1 | Construction Phase | 09/13/2017 A | 10/25/2019 A | 0 | 0 | 0 | Garfield Heights | 17004331
WS-MCIP-2018 | MCIP - 2018 | Maple Heights--Milan/Harlan Drive Sanitary Replacement Project | Construction Phase | 02/18/2019 A | 10/01/2019 A | 0 | 0 | 0 | Maple Heights | 18005835
WS-MCIP-2020 | MCIP - 2020 | Maple Heights - Southwest Sewer District Sewer Improvements Phase 1 | Construction Phase | 03/01/2021 A | 2022-08-30 | 0 | 0 | 0 | Maple Heights | 20003342
WS-MCIP-2017 | MCIP - 2017 | Berea - North End Sewer Rehabilitation | Design Phase | 01/01/2017 A | 08/08/2017 A | 0 | 0 | 0 | Berea | 17003916
WS-MCIP-2018 | MCIP - 2018 | Newburgh Heights--Arlington Avenue Sewer Separation Project | Design Phase | 01/01/2018 A | 05/01/2018 A | 0 | 0 | 0 | Newburgh Heights | 18000955
WS-MCIP-2019 | MCIP - 2019 | Cuyahoga Heights-Nicky Blvd Storm Sewer Extension | Design Phase | 01/01/2019 A | 09/01/2020 A | 0 | 0 | 0 | Cuyahoga Heights | 19000851
WS-MCIP-2020 | MCIP - 2020 | Newburgh Heights - East 41st and Beta Sewer Separation | Design Phase | 01/01/2020 A | 02/17/2021 A | 0 | 0 | 0 | Newburgh Heights | 19007426
WS-MCIP-2021 | MCIP - 2021 | Parma Krueger - Design Only | Design Phase | 01/01/2021 A | 2021-12-31 | 0 | 0 | 0 | Parma | 21000573
WS-MCIP-2017 | MCIP - 2017 | Berea - North End Sewer Rehabilitation | Construction Phase | 10/17/2017 A | 12/18/2018 A | 0 | 0 | 0 | Berea | 17003916
WS-MCIP-2018 | MCIP - 2018 | Newburgh Heights--Arlington Avenue Sewer Separation Project | Construction Phase | 07/24/2018 A | 11/05/2018 A | 0 | 0 | 0 | Newburgh Heights | 18000955
WS-MCIP-2019 | MCIP - 2019 | Cuyahoga Heights-Nicky Blvd Storm Sewer Extension | Construction Phase | 10/01/2020 A | 03/31/2021 A | 0 | 0 | 0 | Cuyahoga Heights | 19000851
WS-MCIP-2020 | MCIP - 2020 | Newburgh Heights - East 41st and Beta Sewer Separation | Construction Phase | 01/30/2022* | 2022-07-11 | 0 | 0 | 0 | Newburgh Heights | 19007426
WS-MCIP-2018 | MCIP - 2018 | South Euclid--2018 Manhole Separation Project | Design Phase | 01/01/2018 A | 03/15/2018 A | 0 | 0 | 0 | South Euclid | 18002625
WS-MCIP-2019 | MCIP - 2019 | Garfield Heights-Midwest Neighborhood Phase 3 | Design Phase | 01/01/2019 A | 08/01/2019 A | 0 | 0 | 0 | Garfield Heights | 18006941
WS-MCIP-2020 | MCIP - 2020 | Pepper Pike - Shaker Boulevard Septic Conversion Project - Phase I | Design Phase | 01/01/2021 A | 02/17/2021 A | 0 | 0 | 0 | Pepper Pike | 20004572
WS-MCIP-2021 | MCIP - 2021 | Shaker Ht Lynnfield & Lomond SSO 11 Control -Design Only | Design Phase | 02/23/2021 A | 2021-12-31 | 0 | 0 | 0 | Shaker Heights | 21000305
WS-MCIP-2017 | MCIP - 2017 | Strongsville - Drake Road, Bowman Drive & Fetzer Drive Sanitary Sewer Project | Construction Phase | 01/01/2017 A | 12/16/2017 A | 0 | 0 | 0 | Strongsville | 17004043
WS-MCIP-2018 | MCIP - 2018 | South Euclid--2018 Manhole Separation Project | Construction Phase | 07/23/2018 A | 08/29/2018 A | 0 | 0 | 0 | South Euclid | 18002625
WS-MCIP-2019 | MCIP - 2019 | Garfield Heights-Midwest Neighborhood Phase 3 | Construction Phase | 12/01/2020 A | 04/07/2021 A | 0 | 0 | 0 | Garfield Heights | 18006941
WS-MCIP-2020 | MCIP - 2020 | Pepper Pike - Shaker Boulevard Septic Conversion Project - Phase I | Construction Phase | 01/30/2022* | 2022-07-11 | 0 | 0 | 0 | Pepper Pike | 20004572
WS-MCIP-2021 | MCIP - 2021 | Shaker Ht Lynnfield & Lomond SSO 11 Control -Design Only | Pre-Verification | 03/29/2021 A | 06/29/2021 A | 0 | 0 | 0 | Shaker Heights | 21000305
WS-MCIP-2018 | MCIP - 2018 | Lyndhurst--Wellington, Cherokee, and Shawnee I & I Reduction | Design Phase | 01/01/2018 A | 06/01/2018 A | 0 | 0 | 0 | Lyndhurst | 18001629
WS-MCIP-2017 | MCIP - 2017 | Cleveland - Rocky River Drive Sewer Replacement Project | Construction Phase | 07/11/2017 A | 10/03/2017 A | 0 | 0 | 0 | Cleveland | 17003924
WS-MCIP-2018 | MCIP - 2018 | Lyndhurst--Wellington, Cherokee, and Shawnee I & I Reduction | Construction Phase | 06/01/2018 A | 12/28/2018 A | 0 | 0 | 0 | Lyndhurst | 18001629
WS-MCIP-2020 | MCIP - 2020 | Cleveland - Edgewater Drive Area Sewer Replacement | Construction Phase | 10/01/2020 A | 05/25/2021 A | 0 | 0 | 0 | Cleveland | 20001285
WS-MCIP-2017 | MCIP - 2017 | Lyndhurst - Irene, Churchill, and Gordon I & I Reduction | Design Phase | 01/01/2017 A | 10/30/2017 A | 0 | 0 | 0 | Lyndhurst | 17003910
WS-MCIP-2018 | MCIP - 2018 | Shaker Heights--Shaker SSO VA9 Fernway Control Project | Design Phase | 01/01/2018 A | 10/10/2018 A | 0 | 0 | 0 | Shaker Heights | 18002624
WS-MCIP-2020 | MCIP - 2020 | South Euclid - Green Road Side Hill Structure Sewer Relocation Project | Design Phase | 01/01/2020 A | 02/17/2021 A | 0 | 0 | 0 | South Euclid | 20003209
WS-MCIP-2017 | MCIP - 2017 | Lyndhurst - Irene, Churchill, and Gordon I & I Reduction | Construction Phase | 11/15/2017 A | 04/10/2018 A | 0 | 0 | 0 | Lyndhurst | 17003910
WS-MCIP-2018 | MCIP - 2018 | Shaker Heights--Shaker SSO VA9 Fernway Control Project | Construction Phase | 03/01/2019 A | 07/11/2019 A | 0 | 0 | 0 | Shaker Heights | 18002624
WS-MCIP-2020 | MCIP - 2020 | South Euclid - Green Road Side Hill Structure Sewer Relocation Project | Construction Phase | 06/25/2021 A | 2021-10-30 | 0 | 0 | 0 | South Euclid | 20003209
WS-MCIP-2019 | MCIP - 2019 | Maple Heights-Various Storm & Sanitary Sewer Repair Project | Design Phase | 01/01/2019 A | 04/01/2020 A | 0 | 0 | 0 | Maple Heights | 18007900
WS-MCIP-2020 | MCIP - 2020 | Summit County - Owen Brown Overflow | Design Phase | 03/26/2020 A | 2021-12-24 | 0 | 0 | 0 | Summit County | 20003343
WS-MCIP-2017 | MCIP - 2017 | Olmsted Twp. - Bagley Road Water & Sewer | Construction Phase | 01/01/2017 A | 07/24/2018 A | 0 | 0 | 0 | Olmsted Twp. | 17003549
WS-MCIP-2019 | MCIP - 2019 | Maple Heights-Various Storm & Sanitary Sewer Repair Project | Construction Phase | 06/06/2019 A | 08/04/2019 A | 0 | 0 | 0 | Maple Heights | 18007900
WS-MCIP-2020 | MCIP - 2020 | Summit County - Owen Brown Overflow | Construction Phase | 05/01/2022* | 2022-12-25 | 0 | 0 | 0 | Summit County | 20003343
WS-MCIP-2019 | MCIP - 2019 | Maple Heights-Various Storm & Sanitary Sewer Repair Project | Pre-Verification | 03/12/2019 A | 05/15/2019 A | 0 | 0 | 0 | Maple Heights | 18007900
WS-MCIP-2020 | MCIP - 2020 | Summit County - Owen Brown Overflow | Pre-Verification | 05/01/2019 A | 07/01/2019 A | 0 | 0 | 0 | Summit County | 20003343
WS-MCIP-2020 | MCIP - 2020 | Summit County - Owen Brown Overflow | Post-Verification | 12/26/2022* | 2023-05-18 | 0 | 0 | 0 | Summit County | 20003343
WS-MCIP-2017 | MCIP - 2017 | Parma - CCDPW - Broadrock Court Sanitary Relief Sewer Connection | Design Phase | 01/01/2017 A | 08/11/2017 A | 0 | 0 | 0 | Parma | 17003613
WS-MCIP-2017 | MCIP - 2017 | Parma - CCDPW - Broadrock Court Sanitary Relief Sewer Connection | Construction Phase | 03/17/2018 A | 07/24/2018 A | 0 | 0 | 0 | Parma | 17003613
WS-MCIP-2020 | MCIP - 2020 | Cleveland - Muriel Ave Sewer Project | Construction Phase | 02/28/2020 A | 05/25/2021 A | 0 | 0 | 0 | Cleveland | 20000696
WS-MCIP-2019 | MCIP - 2019 | Newburgh Heights-E 42 St Sewer Separations | Design Phase | 01/01/2019 A | 08/01/2019 A | 0 | 0 | 0 | Newburgh Heights | 18007343
WS-MCIP-2020 | MCIP - 2020 | Strongsville - Willow Lane Sanitary Sewer Project | Design Phase | 01/01/2020 A | 04/01/2020 A | 0 | 0 | 0 | Strongsville | 19008590
WS-MCIP-2017 | MCIP - 2017 | Parma - Ridge - Ridge Road Septic System Abatement Project | Construction Phase | 02/01/2018 A | 10/31/2018 A | 0 | 0 | 0 | Parma | 17003263
WS-MCIP-2019 | MCIP - 2019 | Newburgh Heights-E 42 St Sewer Separations | Construction Phase | 03/01/2020 A | 06/01/2020 A | 0 | 0 | 0 | Newburgh Heights | 18007343
WS-MCIP-2020 | MCIP - 2020 | Strongsville - Willow Lane Sanitary Sewer Project | Construction Phase | 09/01/2020 A | 2021-07-11 | 0 | 0 | 0 | Strongsville | 19008590
WS-MCIP-2019 | MCIP - 2019 | Newburgh Heights-E 42 St Sewer Separations | Pre-Verification | 06/14/2019 A | 01/01/2020 A | 0 | 0 | 0 | Newburgh Heights | 18007343
WS-MCIP-2019 | MCIP - 2019 | Newburgh Heights-E 42 St Sewer Separations | Post-Verification | 07/16/2020 A | 12/17/2020 A | 0 | 0 | 0 | Newburgh Heights | 18007343
WS-MCIP-2020 | MCIP - 2020 | Garfield Heights - Midwest Phase 4 | Design Phase | 01/01/2020 A | 01/01/2021 A | 0 | 0 | 0 | Garfield Heights | 19007422
WS-MCIP-2020 | MCIP - 2020 | Garfield Heights - Midwest Phase 4 | Construction Phase | 03/29/2021 A | 2021-08-25 | 0 | 0 | 0 | Garfield Heights | 19007422
WS-MCIP-2020 | MCIP - 2020 | Garfield Heights - Midwest Phase 4 | Pre-Verification | 2021-06-30 | 2021-09-28 | 0 | 0 | 0 | Garfield Heights | 19007422
WS-MCIP-2020 | MCIP - 2020 | Garfield Heights - Midwest Phase 4 | Post-Verification | 2021-09-29 | 2021-11-30 | 0 | 0 | 0 | Garfield Heights | 19007422
WS-MCIP-2019 | MCIP - 2019 | Olmsted Falls + Twp-Columbia & Cook Phase 5 | Design Phase | 01/01/2019 A | 07/21/2019 A | 0 | 0 | 0 | Cuyahoga County | 19002184
WS-MCIP-2019 | MCIP - 2019 | Olmsted Falls + Twp-Columbia & Cook Phase 5 | Construction Phase | 09/10/2019 A | 05/03/2021 A | 0 | 0 | 0 | Cuyahoga County | 19002184
WS-MCIP-2019 | MCIP - 2019 | Parma-Broadrock Ct & Old Rockside Septic Systems Abatement | Design Phase | 01/01/2019 A | 12/25/2019 A | 0 | 0 | 0 | Parma | 19000119
WS-MCIP-2019 | MCIP - 2019 | Parma-Broadrock Ct & Old Rockside Septic Systems Abatement | Construction Phase | 06/01/2021 A | 2021-12-31 | 0 | 0 | 0 | Parma | 19000119
WS-MCIP-2019 | MCIP - 2019 | Parma-Valley Villas, York, & State Roads Septic Systems Abatement | Design Phase | 01/01/2019 A | 2021-12-21 | 0 | 0 | 0 | Parma | 19000120
WS-MCIP-2019 | MCIP - 2019 | Parma Heights-Nathan Hale Park Stormwater Basin | Design Phase | 01/01/2019 A | 11/20/2020 A | 0 | 0 | 0 | Parma Heights | 19002176
WS-MCIP-2019 | MCIP - 2019 | Parma Heights-Nathan Hale Park Stormwater Basin | Construction Phase | 07/01/2021* | 2021-11-25 | 0 | 0 | 0 | Parma Heights | 19002176
WS-MCIP-2019 | MCIP - 2019 | Pepper Pike-Gates Mills Blvd Septic Conversion Project | Design Phase | 01/01/2019 A | 09/01/2019 A | 0 | 0 | 0 | Pepper Pike | 18007899
WS-MCIP-2019 | MCIP - 2019 | Pepper Pike-Gates Mills Blvd Septic Conversion Project | Construction Phase | 04/01/2020 A | 08/01/2020 A | 0 | 0 | 0 | Pepper Pike | 18007899
WS-MCIP-2019 | MCIP - 2019 | Shaker Heights-SSO V1BX Control Project | Design Phase | 04/01/2020 A | 08/01/2020 A | 0 | 0 | 0 | Shaker Heights | 19002148
WS-MCIP-2019 | MCIP - 2019 | Shaker Heights-SSO V1BX Control Project | Construction Phase | 08/01/2019 A | 12/25/2019 A | 0 | 0 | 0 | Shaker Heights | 19002148
WS-MCIP-2019 | MCIP - 2019 | Shaker Heights-SSO V1BX Control Project | Pre-Verification | 06/01/2019 A | 08/25/2019 A | 0 | 0 | 0 | Shaker Heights | 19002148
WS-MCIP-2019 | MCIP - 2019 | Shaker Heights-SSO V1BX Control Project | Post-Verification | 10/15/2020 A | 12/31/2020 A | 0 | 0 | 0 | Shaker Heights | 19002148
WS-MCIP-2019 | MCIP - 2019 | Walton Hills-Egbert Rd Sanitary Force Main Replacement | Design Phase | 01/01/2019 A | 07/01/2019 A | 0 | 0 | 0 | Walton Hills | 19000886
WS-MCIP-2019 | MCIP - 2019 | Walton Hills-Egbert Rd Sanitary Force Main Replacement | Construction Phase | 11/01/2019 A | 03/01/2020 A | 0 | 0 | 0 | Walton Hills | 19000886
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Seven Hills- Hemlock Creek Watershed Utiltiy Improvement | 01/01/2017 A | 12/20/2019 A | 1090000 | 1035500 | 0 | Seven Hills | 17004258
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Village of Richfield--Briarwood Area Wastewater Pump Stations | 01/01/2018 A | 2022-05-19 | 891500 | 0 | 891500 | Village of Richfield | 18004746
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Berea - North End Phase 2 | 04/15/2020 A | 2022-12-20 | 688684 | 0 | 688684 | Berea | 20000057
WS-MCIP-2021 | MCIP - 2021 | Project Budget | Lorain - Westview I&I Remediation | 06/01/2021 A | 2021-10-25 | 359300 | 0 | 359300 | Lorain County | 20007975
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Olmsted Falls - Columbia & Cook Sanitary Sewer Project Phase 5 | 01/01/2017 A | 05/18/2020 A | 600000 | 570000 | 0 | Olmsted Falls | 17004905
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Mayfield Village--Thornapple Drive & Robley Lane New Sanitary Sewer | 01/01/2018 A | 05/20/2018 A | 750000 | 712500 | 0 | Mayfield Village | 18001614
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Brecksville: Chippewa Road Sanitary Sewer Project | 01/01/2019 A | 2023-06-30 | 1500000 | 0 | 1500000 | Brecksville | 18007901
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Summit County-Macedonia - Crow Berkshire Private I/I | 03/02/2020 A | 2023-02-25 | 549000 | 0 | 549000 | Summit County | 20001661
WS-MCIP-2021 | MCIP - 2021 | Project Budget | Maple Heights Southwest Area - Design Only | 03/01/2021 A | 2022-10-15 | 1021887 | 0 | 1021887 | Maple Heights | 21002394
WS-MCIP-2017 | MCIP - 2017 | Project Budget | South Euclid - Grosvenor Infrastructure Improvement, Phase 2 | 01/01/2017 A | 07/11/2017 A | 300000 | 300000 | 0 | South Euclid | 17003621
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Parma--Brookdale/Broadview Septic Systems Abatement Project | 01/01/2018 A | 12/01/2019 A | 160160 | 0 | 0 | Parma | 18003716
WS-MCIP-2019 | MCIP - 2019 | Project Budget | CCDPW: Bagley and Cook Roads Sewer Connections | 01/01/2017 A | 2021-12-30 | 127500 | 0 | 127500 | Cuyahoga County | 19000821
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Parma - Sprague Road | 2021-07-01 | 2022-12-25 | 421847 | 0 | 421847 | Parma | 19008576
WS-MCIP-2021 | MCIP - 2021 | Project Budget | South Euclid - Oakmount Rd | 01/01/2020 A | 2021-10-31 | 365973 | 0 | 365973 | South Euclid | 21002397
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Newburgh Heights - East 54th and Brow Avenue Sewer Separation | 01/01/2017 A | 10/30/2017 A | 400000 | 400000 | 0 | Newburgh Heights | 17002792
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Garfield Heights--Midwest Neighborhood Storm/Sanitary Sewer Recon. Phase 2 | 01/01/2018 A | 10/01/2019 A | 1000000 | 143131 | 0 | Garfield Heights | 18000954
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Cleveland Heights - Delamere Drive Basement Flooding Relief | 03/01/2021 A | 2021-10-01 | 1337898 | 0 | 1337898 | Cleveland Heights | 19008773
WS-MCIP-2021 | MCIP - 2021 | Project Budget | East Cleveland Wheeler Ave - Design Only | 01/01/2021 A | 2021-12-31 | 302340 | 0 | 302340 | East Cleveland | 21000321
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Garfield Heights - NW Neighborhood Sanitary/Storm Sewer Reconstruction Phase 1 | 01/01/2017 A | 10/25/2019 A | 717533 | 696516.33 | 0 | Garfield Heights | 17004331
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Maple Heights--Milan/Harlan Drive Sanitary Replacement Project | 01/01/2018 A | 10/01/2019 A | 153544.65 | 0 | 0 | Maple Heights | 18005835
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Maple Heights - Southwest Sewer District Sewer Improvements Phase 1 | 03/01/2021 A | 2022-08-30 | 1135180 | 0 | 1135180 | Maple Heights | 20003342
WS-MCIP-2021 | MCIP - 2021 | Project Budget | Parma Green Acres - Design Only | 01/01/2021 A | 2021-12-31 | 78000 | 0 | 78000 | Parma | 21000571
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Berea - North End Sewer Rehabilitation | 01/01/2017 A | 12/18/2018 A | 735023 | 735023 | 0 | Berea | 17003916
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Newburgh Heights--Arlington Avenue Sewer Separation Project | 01/01/2018 A | 11/05/2018 A | 178000 | 178000 | 0 | Newburgh Heights | 18000955
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Cuyahoga Heights: Nicky Blvd Storm Sewer Extension | 01/01/2019 A | 03/31/2021 A | 303413.25 | 0 | 0 | Cuyahoga Heights | 19000851
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Newburgh Heights - East 41st and Beta Sewer Separation | 2022-01-30 | 2022-07-11 | 1018424 | 0 | 1018424 | Newburgh Heights | 19007426
WS-MCIP-2021 | MCIP - 2021 | Project Budget | Parma Krueger - Design Only | 01/01/2021 A | 2021-12-31 | 260000 | 0 | 260000 | Parma | 21000573
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Strongsville - Drake Road, Bowman Drive & Fetzer Drive Sanitary Sewer Project | 01/01/2017 A | 12/16/2017 A | 617165 | 617165 | 0 | Strongsville | 17004043
WS-MCIP-2018 | MCIP - 2018 | Project Budget | South Euclid--2018 Manhole Separation Project | 01/01/2018 A | 08/29/2018 A | 306130.75 | 306130.75 | 0 | South Euclid | 18002625
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Garfield Heights: Midwest Neighborhood Phase 3 | 01/01/2019 A | 04/07/2021 A | 686124.42 | 0 | 0 | Garfield Heights | 18006941
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Pepper Pike - Shaker Boulevard Septic Conversion Project - Phase I | 2022-01-30 | 2022-07-11 | 1442375 | 0 | 1442375 | Pepper Pike | 20004572
WS-MCIP-2021 | MCIP - 2021 | Project Budget | Shaker Ht Lynnfield & Lomond SSO 11 Control -Design Only | 02/23/2021 A | 2021-12-31 | 112500 | 0 | 112500 | Shaker Heights | 21000305
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Cleveland - Rocky River Drive Sewer Replacement Project | 07/11/2017 A | 10/03/2017 A | 1040000 | 1040000 | 0 | Cleveland | 17003924
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Lyndhurst--Wellington, Cherokee, and Shawnee I & I Reduction | 01/01/2018 A | 12/28/2018 A | 84191.92 | 84191.92 | 0 | Lyndhurst | 18001629
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Cleveland - Edgewater Drive Area Sewer Replacement | 10/01/2020 A | 05/25/2021 A | 1300000 | 0 | 0 | Cleveland | 20001285
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Lyndhurst - Irene, Churchill, and Gordon I & I Reduction | 01/01/2017 A | 04/10/2018 A | 249270 | 161234.48 | 0 | Lyndhurst | 17003910
WS-MCIP-2018 | MCIP - 2018 | Project Budget | Shaker Heights: Shaker SSO VA9 Fernway Control Project | 01/01/2018 A | 07/11/2019 A | 400000 | 263321.18 | 0 | Shaker Heights | 18002624
WS-MCIP-2020 | MCIP - 2020 | Project Budget | South Euclid - Green Road Side Hill Structure Sewer Relocation Project | 01/01/2020 A | 2021-10-30 | 194605 | 0 | 194605 | South Euclid | 20003209
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Olmsted Twp. - Bagley Road Water & Sewer | 01/01/2017 A | 07/24/2018 A | 500000 | 500000 | 0 | Olmsted Twp. | 17003549
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Maple Heights: Various Storm & Sanitary Sewer Repair Project | 01/01/2019 A | 08/04/2019 A | 599950 | 0 | 0 | Maple Heights | 18007900
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Summit County - Owen Brown Overflow | 03/26/2020 A | 2023-05-18 | 475000 | 0 | 475000 | Summit County | 20003343
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Parma - CCDPW - Broadrock Court Sanitary Relief Sewer Connection | 01/01/2017 A | 07/24/2018 A | 250000 | 250000 | 0 | Parma | 17003613
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Cleveland - Muriel Ave Sewer Project | 02/28/2020 A | 05/25/2021 A | 497000 | 0 | 0 | Cleveland | 20000696
WS-MCIP-2017 | MCIP - 2017 | Project Budget | Parma - Ridge - Ridge Road Septic System Abatement Project | 02/01/2018 A | 10/31/2018 A | 340036 | 340036 | 0 | Parma | 17003263
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Newburgh Heights: E 42 St Sewer Separations | 01/01/2019 A | 12/17/2020 A | 291303 | 0 | 0 | Newburgh Heights | 18007343
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Strongsville - Willow Lane Sanitary Sewer Project | 09/01/2020 A | 2021-07-11 | 624750 | 0 | 624750 | Strongsville | 19008590
WS-MCIP-2020 | MCIP - 2020 | Project Budget | Garfield Heights - Midwest Phase 4 | 01/01/2020 A | 2021-11-30 | 1224132.5 | 0 | 1224132.5 | Garfield Heights | 19007422
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Olmsted Falls + Twp: Columbia & Cook Phase 5 | 01/01/2019 A | 09/10/2019 A | 1090500 | 0 | 0 | Cuyahoga County | 19002184
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Parma: Broadrock Ct & Old Rockside Septic Systems Abatement | 06/01/2021 A | 2021-12-31 | 260000 | 0 | 260000 | Parma | 19000119
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Parma: Valley Villas, York, & State Roads Septic Systems Abatement | 01/01/2019 A | 2021-12-21 | 480000 | 0 | 480000 | Parma | 19000120
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Parma Heights: Nathan Hale Park Stormwater Basin | 01/01/2019 A | 2021-11-25 | 1000000 | 0 | 1000000 | Parma Heights | 19002176
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Pepper Pike: Gates Mills Blvd Septic Conversion Project | 01/01/2019 A | 08/01/2020 A | 838280.8 | 0 | 0 | Pepper Pike | 18007899
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Shaker Heights: SSO V1BX Control Project | 04/01/2020 A | 12/31/2020 A | 425000 | 0 | 0 | Shaker Heights | 19002148
WS-MCIP-2019 | MCIP - 2019 | Project Budget | Walton Hills: Egbert Rd Sanitary Force Main Replacement | 01/01/2019 A | 03/01/2020 A | 321500 | 0 | 0 | Walton Hills | 19000886